## OSS Investigation Process_backu (hidden)
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Input | Ouput | Remarks
1 | Ticket Handling Process |  | Client | New | 1) Target OSS 2) OSS requirement 3) Duration or deadline | New Ticket | Tracker: Consultancy
PM/PL
|  |  | PM/PL | Assigned | New Ticket | Assgined ticket | If task involves multiple OSS investigation, PM/PL should create subtasks such that there is 1 subticket for 1 OSS.
2 | Estimation Process Review Process |  | Engineer | InProgress | Requirements described in ticket or uploaded requirements document | Requirements list | Engineer collects the OSS requirements based on the ticket
|  |  | Engineer | Feedback | Q&A List | Email for clarification Updated redmine ticket | Member will solicit additional requirements from the client
|  |  | Client | Feedback | Email for clarification Updated redmine ticket | Q&A Response
|  |  | Engineer | Feedback | Q&A Response | Follow up Q&A / Confirmed Q&A | Review the answers/comments to Q&A Make a follow-up question if there are still unclear parts or proceed to Estimation if there Q&A is already OK
|  |  | Engineer | InProgress | Requirements list | Initial Research Notes | Perform an initial research based on requirement to use as basis for estimation Check if there is an existing infromation in OSS wiki.
|  |  | Engineer | InProgress | Requirements list Initial Research Notes | Activity List and Schedule | Create an investigation plan and its schedule
|  |  | PM/PL | InProgress | Requirements List Activity List and Schedule Initial Assessment | Review Comments | Review the plan and schedule in reference to requirements list
|  |  | Engineer | Feedback | Requirements List Activity List and Schedule Initial Assessment | Updated ticket | Update the ticket with the initial investigation and schedule
|  |  | Client | Feedback | Updated ticket (Proposal) | Updated ticket (comments/approval) | Client reviews the initial assessment, schedule and requirements list Client should give comments if there are unclear/incorrect items or give approval if its client agrees with the proposal
|  |  | Engineer | InProgress | Requirements List Activity List and Schedule Initial Assessment | Investigation Report Research Documentation | Refer to Investigation Process for the details
3 | Investigation Process Review Process
|  |  | Client | Feedback | Investigation Report Research Documentation | Client Confirmation or Client Comments | Client reviews the investigation report and research documentation If client has comments or additional requests, the ticket will be updated with the additional comments/requirements. And the process will go back to investigation. If all are OK wiki will be updated and the ticket will be closed.
4 | Wiki Update Process |  | Engineer | Resolved | Research Documentation | New Wiki Site or Updated Wiki Site | Refer to Knowledge Management Process on how to create/update wiki page
5 | Ticket Handling Process |  | PM/PL | Closed | Client Confirmation/Decision | Closed Ticket
|  |  | OSS evaluation/Investigation |  | Problem
|  | Planning and Estimation | Gathering initial details |  | Replication
Duplicate Issue
Estimate
Overall Task Flow
| Processes Involved | Flow | Action | Status
| Ticket Handling Process |  | Create Ticket | New
0%
|  |  | Assign Ticket | Assigned
0%
| Estimation Process |  | Update Ticket | InProgress
|  |  | 1-99% | Feedback
Done?
|  | 20% |  | Resolved?
Cancelled?
Rejected?
Investigation process
90%
Wiki Process
95%
|  |  | Close Ticket | Closed
| Ticket Handling Process |  | 100%
Ticket Registration
Ticket Assignment
Perform Estimation
no modifications needed
some modifications needed
re-investigate
Gather Requirements
cancel request
Perform Initial Research
Perform Detailed Investigation
Update Ticket
Review Req List and Schedule
Client Confirmation
estimate is not OK
Client Assessment
Wiki Update
Close Ticket
cancel request
Request additional info from client
Client provides response to clarification
Verifies answers to Q&A
Info sufficient
Need additional details
Need additional details
Info sufficient
Ticket Registration
Ticket Assignment
Initial Assessmenet and Estimation
Perform Detailed Investigation
Wiki Update
Close Ticket

## Title Page
NEC Telecom Software Philippines, Inc. |  | OSS Benchmarking Process | Registration No.
|  |  | Version No. | 00.00.01
|  |  | Date | 2017-06-15
|  |  | No. of Sheets | 4
|  |  | Approved | Reviewed | Prepared
NSP-May
Table of Contents
Sheet No. | Sheet Title
1 | Title Page
2 | Revision History
3 | Introduction
4 | OSS Benchmarking Process
5 | OSS Benchmarking Template

## Revision History
Revision History
Version No. | Date | Author | Reviewer | Revision Summary
00.00.01 | 2017-06-15 | NSP-May |  | · Draft

## Introduction
OSS Patch Verification Process
1. Overview
The OSS Benchmarking Process serves as a guide in performing Benchmarking of similar OSS. It aims to document the comparison of the different OSS
with the same purpose or use to be able to guide clients in selecting which OSS will best fit their current needs.
2. Purpose
To provide a process and/or guidelines on how to perform OSS Benchmarking.
3. Scope
This process is applicable to OSS Benchmarking activities of the OSS Team.
4. Definition and Acronyms
| Term | Definition
| OSS | Open-Source Software - is a software with source code that anyone can inspect, modify, and enhance.
This symbol depicts another Process or Subprocess within this document or in another document. This symbol is also used as another Task or Activity within this document or in another document.
This symbol is the tasks within this Process or Subprocess.
| Benchmarking (OSS) | Benchmarking is the comparison of different OSS with similar purpose, use, functionalities, features, etc. This comparison will help aide the clients of OSS Technical Center in deciding which is the best OSS for their use.
5. Roles and Responsibilities
| Role | Responsibility
| Project Manager | • Responsible for performing the tasks assigned to Incharge PM
| Project Leader | • Responsible for performing the tasks assigned to Incharge PL
| Project Member | • Responsible for performing the tasks assigned to Incharge OSS Engineer
| Client | • Responsible for performing the tasks assigned to Incharge Client
5. References
None.
Task
Process or Subprocess
Task or Activity

## OSS Benchmarking
OSS Benchmarking Process
|  | Entry Criteria: | Benchmarking is requested by the client to be able to compare different OSS with similar purpose, use, functionalities, features, etc. to help decide which is the best OSS fit for their use.
|  | Exit Criteria: | The Benchmarking document is published in the NSP OSS website.
| Task # | SubProcess | Process Flow | Incharge | Ticket Status | Input | Ouput | Details
| 1 | OSS Benchmarking |  | OSS Engineer | InProgress | Updated Ticket | List of OSS for Benchmarking | 1. Selection of OSS for Benchmarking: a. If client have listed the OSS for Benchmarking then use the client's list, and if applicable propose additional OSS to client also. b. If client have no listed OSS for Benchmarking, perform initial investigation on similar OSS that we can propose to the client for Benchmarking. 2. After the List of OSS for Benchmarking is done, proceed to the next task.
|  |  |  | OSS Engineer | InProgress | Updated Ticket | For each OSS for Benchmarking, any of the OSS Task Output as follows is done: - Investigation Report - Problem Investigation Report - Evaluation Report - Consulting Support Report - Issue - Q&A | For each of the OSS for Benchmarking listed, perform the type of task that will be appropriate to gather all of the OSS details necessary (eg. overview, purpose, function, features etc.). Choose the appropriete task from the list of processes below: - Investigation Process - Problem Investigation Process - Evaluation Process - Consulting Support Process - Issue Management Process - Q&A Support Process
|  |  |  | OSS Engineer | InProgress | For each OSS for Benchmarking, any of the OSS Task Output is available: - Investigation Report - Problem Investigation Report - Evaluation Report - Consulting Support Report - Issue - Q&A | Benchmarking Document | 1. Using the output for each OSS for Benchmarking from the previous task, create the Benchmarking document. Refer to the sheet "OSS Benchmarking Template" on how to document the OSS Benchmarking. 2. Update the Benchmarking document in case there are necessary updates after review is done.
|  |  |  | PM/PL Client OSS Engineer | InProgress | Benchmarking Document ready for Review | Benchmarking Document RRC | Review the Benchmarking document based on completeness and correctness of the comparison of the different OSS for Benchmarking. During review refer to the review POV in the sheet "OSS Benchmarking Template", section "OSS Benchmarking Review POV".
In case update is necessary after review, perform the Create/Update Benchmarking document task.
|  |  |  | OSS Engineer | InProgress | Reviewed and Approved Benchmarking Document | Published Benchmarking Document in the NSP OSS Website | Publish the Benchmarking document in the NSP OSS Website.
Create/Update the Benchmarking document
Review the
Benchmarking document
For each OSS for Benchmarking, perform:
OSS Knowledge Management Process:
Knowledge Acquisition
End
Publish the
Benchmarking Document
Update needed after review?
No
Yes
List OSS for Benchmarking

## Investigation Process (hidden)
Input | Schedule
Requirements List
Output | Investigation Report
Research Documentation
1 |  | Collect information/references from
1) OSS Wiki Site (if available)
2) Reference documents from other NSP project groups
3) Official OSS website
4) Internet (other references)
2 |  | Read and study the collected references (create notes)
Check the strong and weak points of the OSS
Perform analysis if OSS is suitable to use or if there are better OSS
Check if references gathered has enough information for the OSS requirements
If not, search for additional material and study them
Record all issues/problems known during study/research
3 |  | Check harware requirements if it is available in OSS Tech Center
Check software requirements if it can be acquired from internet(free) or from client(with license)
If hardware/software requirements is not available, arranged use of client environment
Get commitment on date and time of environment use by OSS Tech Center
If hardware/software requirements is available, download the OSS and other softwares
Install OSS either from source or repository
Install the OSS using the mandated method of the client (yaml, rpm, ,etc)
Record all issues/problems known during study/research
4 |  | Configure the OSS based on the indicated setup in requirements list
If there are no indicated setup in the requirements list, decide the best setup based on the requirements
Record all issues/problems known during study/research
5 |  | Create test specification
|  | Execute test items |  |  | Are we going to use tool?
|  | Collect evidence during testing (screenshot, logs, packet capture) |  |  | What tool to use?
Record all issues/problems known during study/research
6 |  | Create investigation report
Organize notes to cater to wiki sections/contents or customer specified output
7 |  | Check if investigation report is complete based on requirements
Check if documentation is enough
Refer to review process sheet for the details of review procedure/guidelines
8 |  | Update ticket with investigation report and research documentation
9 |  | Client will assess if investigation report is correct and complete
Ticket will be updated whether client agrees to the investigation report or updated based on client comments
It is possible that re-investigation is needed based on client comments or
it is possible that the request will be cancelled or
the ticket will be closed because investigation report already satisfies the client.
10 |  | Wiki site will be created/updated based on the investigation performed by the engineer.
11 |  | The request is cancelled as decided by client
OSS Default Contents for OSS Investigation
M/O | Description | Remarks
M | OSS Overview | This is a mandatory section. Discusses the short description about the OSS.
M | Architecture | This is a mandatory section. A diagram on showing its modules and its relationships.
M | Features and Functionalities | This is a mandatory section. Enumerates and discusses the OSS functionalities and features.
M | System Requirements | This is a mandatory section. List the hardware and software requirements of the OSS. Also list down the software dependencies.
M | Version Information | This is a mandatory section. List down the OSS versions and its supported features(or limitations).
M | Installation Procedure/Guide | This is a mandatory section. An installation guide for its supported setup.
M | System Configurations | This is a mandatory section. List/Diagrams of the different configurations supported by the OSS.
M | Use case | This is a mandatory section. Use cases supported by the OSS.
M | Limitations/Known issues | This is a mandatory section. Known bugs/limitations of the OSS.
M | License | This is a mandatory section. License information of the OSS. OSS can have a separate site for different types of License. And the Licence type can just be mentioned in the OSS overview.
O | Performance | This is an optional section but will become mandatory if indicated by client. Performance data can collected from official OOS website or benchmarking website or from actual testing.
O | Reliability | This is an optional section but will become mandatory if indicated by client. Realiability data can collected from officail OSS website or by research to other references.
O | Availability | This is an optional section but will become mandatory if indicated by client. Availability data can collected from officail OSS website or by research to other references.
O | Security | This is an optional section but will become mandatory if indicated by client. Security data can collected from officail OSS website or by research to other references.
O | Modifiability | This is an optional section but will become mandatory if indicated by client. Modifiability data can collected from officail OSS website or by research to other references.
O | Portability | This is an optional section but will become mandatory if indicated by client. Portability data can collected from officail OSS website or by research to other references.
O | Scalability | This is an optional section but will become mandatory if indicated by client. Scalability data can collected from officail OSS website or by research to other references.
O | System Components | This is an optional section but will become mandatory if indicated by client. System Components can collected from officail OSS website or by research to other references.
O | Technologies used | This is an optional section but will become mandatory if indicated by client. Technology used can collected from officail OSS website or by research to other references.
Overall Task Flow
| Processes Involved | Flow | Action | Status
| Ticket Handling Process |  | Create Ticket | New
0%
|  |  | Assign Ticket | Assigned
0%
| Estimation Process |  | Update Ticket | InProgress
|  |  | 1-99% | Feedback
Done?
|  | 20% |  | Resolved?
Cancelled?
Rejected?
Investigation process
90%
Wiki Process
95%
|  |  | Close Ticket | Closed
| Ticket Handling Process |  | 100%
How to Perform Review
PM/PL
Group
Peer
Client
Walkthrough
Desk Review
Self Check
POV
Spelling&Grammar
Content Relevance Review
Completeness (template as basis?)
Collect Information or References
Study and Record Notes
Install OSS
Configure OSS
Installation Verification
Create Investigation Ouput
Review/Confirmation
Update Ticket
some modifications needed
no modifications needed
Client Confirmation
some modifications needed
Reflect investigation result to Wiki
Cancel Request
Ticket Registration
Ticket Assignment
Initial Assessmenet and Estimation
Perform Detailed Investigation
Wiki Update
Close Ticket

## Estimation Process (hidden)
Pls. use NSP08-00000-TMP006_Project Estimation Template.xls and NSP08-00000-GDL003_Project Estimation Guideline.doc

## Investigation Process_old (hidden)
How to perform investigation/research
Phases | Description
Req Development | Determine the scope of the research based on information in the ticket
If the information in the ticket is not enough, inquire to the client
| Create a requirement list and get client confirmation [email, ticket update, face-to-face review] |  |  |  | Steps
| Perform initial research for estimation and feasibility check of client requirement and specified OSS |  |  |  | Determine the research scope
Research | Collect information regarding the target OSS from existing documents |  |  |  | Determine mandatory and optional requirements
| Collect information from other project groups |  |  |  | Determine the timeline
| Collect information from internet (visit official website of OSS, visit other sites for reference, check reviews/comparisons) |  |  |  | Write a research questions
| Check completeness of acquired information using OSS investigtion template [refer to Appendix A. OSS Investigation Template] |  |  |  | Collect possible sources
| Check completeness of information based on client mandated output (if available) |  |  |  | Begin reading in detail
| Commit notes, output document daily (for PM/PL desk review) |  |  |  | Take notes on what you read
| Perform installation/configuration of OSS based on customer environment (if there is time and environment is available) |  |  |  | Evaluate your information (installation/configuration/testing)
Record all the sites used as reference
Concentrate information collection based on the requirements list
Record known issues encountered for documentation
Analysis | Perform feasibility analysis of requirements based on acquired OSS information
Create an output document based on customer requirements or customer requested output
How to check successful installation
How to check successful configuration
| Operation Management | Market Research | Description | Method
ViewPoints/Document Contents | Mandatory | Mandatory | OSS Overview
| Mandatory | Mandatory | Architecture
| Mandatory | Mandatory | Features and Functionalities
| Mandatory | Mandatory | System Requirements
| Mandatory | Mandatory | Version Information
| Mandatory | Mandatory | Installation Procedure/Guide
| Mandatory | Mandatory | System Configurations
| Mandatory | Mandatory | Use case
| Mandatory | Mandatory | Limitations/Known issues
| Mandatory | Mandatory | License
| Optional | Mandatory | Performance | Collect performance information through website research For advance performance data collection refer to <document name here>
| Optional | Mandatory | Reliability
| Optional | Mandatory | Availability
| Optional | Mandatory | Security
| Optional | Mandatory | Modifiability
| Optional | Mandatory | Portability
| Optional | Mandatory | Scalability
| Optional | Mandatory | System Components
| Optional | Mandatory | Technologies used
Research | Notes
References (books, url)
Testing | Screenshot
Logs
| Packet Capture |  |  |  |  | Check the wiki | Collect Basic Information
Collect Advance Information (if available)
Check the ticket for the requirements stated by the client
Create a requirements list
Solicit from client if there are other needed information mentioned (ticket, email, lync)
There should be evidence for the solicited requirements, either email or recorded conversation
Perform a short research about the feasibility of the request
Create an estimate to check if the requested end date can be met
Update the ticket with initial investigation result and estimate
If the end scope is too big to finish on the required date
Suggest a new schedule so on when it can be finished
Or list down requirements that can be excluded so that the activity can fit on the given schedule
When the schedule and scope are agreed with the client
Perform detailed investigation based on the requirements list
Refer to Knowledge Management Process on how to perform detailed investigation
how to determine if the information is not enough
how to collect data?
write in redmine (not adivisable for research activities)
write to a new document, store in repo and note the location in redmine ticket
write to a new document and attach to redmine ticket
Requirements
Gathering
Perform Initial Investitgation
Create an Estimate
Feedback to client
Perform Detailed Investigation
Investigation
Process
Check the OSS Wiki Site
Check the official OSS Site
Check reference documents from other NSP groups
Check other Internet sites for reference
Check sites for OSS reviews or comparison
Perform Installation and configuration

## OSS Investigation Process_old (hidden)
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Input | Ouput | Remarks
1 | Ticket Handling Process |  | Client | New | Target OSS | New Ticket | New OSS investigation request Ticket can be of the following type: Consultancy
Duration/Delivery Date
Intended Usage, Required Output
|  |  | PM/PL | New |  |  | New OSS for knowledge building is identified Ticket can be of the following type: Consultancy
|  |  | PM/PL | Assigned |  |  | Assigns developer to investigate the ticket
2 | Estimation Process Review Process |  | Developer |  | Client Requirements | Initial Investigation Result | Perform initial investigation and create estimate/schedule for the new OSS | What will be the status when developer starts initial investigation
Estimate
|  |  | PM/PL |  | Initial Investigation Result | Review Comments | Review estimate and schedule
Estimate
|  |  | Developer | Feedback |  | Updated Investigation/ | Update ticket with schedule/estimate and initial information
Updated Estimate
|  |  | Client | Feedback |  |  | Check if estimate is OK, decide to continue or not based on initial information
Ticket is updated with
client feedback
3 | Investigation Process Review Process |  | Developer | InProgress | Client Requirements | Research Report ( Customer | Perform research/investigation
or OSS default format)
|  |  | PM/PL | InProgress |  |  | Perform review based on investigation result
[5 empty] | Research Report | Review Comments
|  |  | Developer | InProgress |  | Updated Research Report | Perform rework based on review comments
|  |  | PM/PL | Done |  |  | Perform confirmation of review comments
|  |  | Client | Resolved |  |  | Client agrees with the investigation result and there are no futher requests/comments
4 | Wiki Process |  | Developer | Resolved |  | New Wiki Site | Create/Update Wiki based on the approved contents of investigation
or updated wiki site
5 | Ticket Handling Process |  | PM/PL | Closed |  |  | Close Ticket
Ticket Registration
Ticket Assignment
Research/Investigation
Review
Rework
Confirmation
Create/Update Wiki
Close Ticket
Perform Estimation
Update Ticket
Review Estimate
Confirm Estimate
estimate is not OK
estimate is OK
cancel request
proceed with investigation
for re-estimation
no modifications needed
some modifications needed
some modifications needed
no modifications needed
Close Ticket
Client confirmation

## OSS Benchmarking Template
OSS Benchmarking Template
| Purpose for Benchmarking | <Describe briefly the use/purpose of the similar OSS's for benchmarking>
| Scope of Benchmarking | <Describe briefly the scope of benchmarking the similar OSS's>
OSS Benchmarking Details
| OSS Criteria | OSS Sub-criteria | <OSS A> | <OSS B> | <OSS C> | <OSS D>
OSS Overview
System Requirements
Version Information
System Configuraiton
License
Limitations/Known Issues
| Features and Functionalities | Feature & Functionalities A
Feature & Functionalities B
Feature & Functionalities C
Feature & Functionalities D
Feature & Functionalities E
Feature & Functionalities F
| Non Functional Requirements | NFR A
NFR B
NFR C
NFR D
<< Remove all contents from this line and below for the OSS Benchmarking >>
OSS Benchmarking Guide
OSS Benchmarking Template Guideline
1. The OSS Criteria and OSS Sub-criteria listed above are suggested criteria only. Please use all criteria applicable to the OSS that will be benchmarked.
2. You can use brief description of the specific criteria for each OSS for Benchmarking. You can also use markings (e.g. Legend: "O" or "X") to indicate if a criteria is supported or not by the OSS.
3. Take note that not all criteria listed may be supported in each of the OSS for Benchmarking, in this case you can mark it as "NA" or use defined markings similar to no. 2 above, whichever is applicable.
4. Consider adding necessary NFR's in the criteria (eg. Performace, Security, Availability, etc.) that is applicable for the OSS's for Benchmarking.
OSS Benchmarking Review POV
| a. "OSS Criteria" column | Ensure that all OSS Criteria that is necessary for the OSS Benchmarking is listed in the "OSS Criteria" column.
| b. "OSS Sub-criteria" column | Ensure that all OSS Sub-criteria that is necessary for the OSS Benchmarking is listed in the "OSS Sub-criteria" column.
| c. "OSS Benchmarking Details" columns | Ensure that the contents of each "OSS Benchmarking Details" (e.g. "Benchmarking <OSS A>") are completely and correctly written, except if this specific "OSS Criteria" or "OSS Sub-criteria" is not present or not applicable in this OSS.