## Title Page
NEC Telecom Software Philippines, Inc. |  | OSS Issue Management Process | Registration No.
|  |  | Version No. | 00.00.01
|  |  | Date | 2017-04-12
|  |  | No. of Sheets | 4
|  |  | Approved | Reviewed | Prepared
NSP-fasano 2017/04/12
Table of Contents
Sheet No. | Sheet Title
1 | Title Page
2 | Revision History
3 | Introduction
4 | Issue Management Process

## Revision History
Revision History
Version No. | Date | Author | Reviewer | Revision Summary
00.00.01 | 2017-04-12 | NSP-fasano |  | · Draft

## Introduction
OSS Issue Management Process
1. Purpose
To provide a process on how to manage and resolve issues encountered during knowledge acquisition.
2. Scope
This process is applicable to all knowledge acquisition activities of OSS Team
3. Definition and Acronyms
| Term | Definition
| OSS | Open-Source Software - is a software with source code that anyone can inspect, modify, and enhance.
| Issue | An event, a topic, a problem or anything that needs resolution for the project or an activity to proceed successfully.
| SOW | Statement of Work A formal document that defines the deliverables and the activities or services that needs to be performed inorder to satisfy these deliverables. It usually includes the quality, cost and delivery requirements for its implementation.
| RA | Requirements Analysis The determination of product-specific performance and functional characteristics based on analyses of customer needs, expectations, and constraints; operational concept; projected utilization environments for people, products, and processes; and measures of effectiveness. CMMI for Dev 1.2
| Project Plans | This is composed of a set of documents for planning and monitoring which are the following: Project Plan 1, Project Plan 2, Process List, CM Plan and Test Plan.
| Pinit | Project Initiation The process where initial negotiations with prospective client and NSP management are performed for a proposed software project for NSP. This process involves creating highlevel estimates, sending quotations to client, checking for project feasibility in NSP, etc.
| PMO Project Review PPR | - An activity to determine soundness or satisfactoriness of a project’s high-level plans. - Project Reviews may occur during Project Initiation prior to committing to a transaction with the customer or during Project Planning after receiving a Purchase Order from the customer.
| Historical Data | Project data collected data from previous project cycles used for estimating size, effort, quality and other relevant parameters of new project. Source of data: QA (collated data from different projects) Project team (data from previous project)
| Accountability | Accepting responsibility and being answerable to the actions taken and to the output of process tasks.
| Responsibility | An obligation to do or ensure proper implementation of process tasks in order to produce the desired output.
4. Roles and Responsibilities
| Role | Responsibility
| Project Manager | • The project manager assigned to handle the project
• Reviews the estimates and project plan
• Negotiates with the client
| Project Leader | • Creates the estimates and the project plan
| Project Member | • Responsible for providing inputs necessary for project planning (e.g. provide estimates) and commits to the plan
5. References
None.

## Issue Management Process
Entry Criteria: | An issue was encountered during installation/configuration of OSS | Add criteria per research/installation/source code trace
Exit Criteria: | Issue was resolved and know-how was documented. | Add criteria per research/installation/source code trace
Task | Process Flow | Incharge | Approver | Ticket Status | Remarks
1 |  | MIC |  |  | ▶ Using keywords, search the <knowledge-based tool> for similar issue being encountered.
▶ Create guidelines/procedure how to perform search in <redmine> or <knowledge-based tool>
▶ Make sure that all related tickets were investigated and understood.
▶ Perform countermeasure.
How to confirm that the issue is solved?
What criteria to consider? Was the issue resolved?
Was there no collateral issue generated due to the implementation of countermeasure?
2 |  |  |  |  | Refer to Issue Registration Guideline.xlsx (to be created)
This will address what and how to create an issue ticket in <redmine>.
What information to input in the ticket.
What other files needed like logs, config files
Investigate issue:
A. Config - check if all previous steps was followed accordingly
B. Network Setup
C. HW and SW Setup
- Is the HW and SW resource indicated in Installation Manual followed? (use of VMs instead of PMs)
- Was the setup of HW and SW resources correct? (memory, # of cpus)
Perform root cause analysis.
criteria for categorization and prio
How to determine?
> Search the internet
> Ask persons with experience to the OSS
> Ask in community
> Source code trace
Assess each countermeasures, its pros and cons
What are the risks associated to each countermeasure
Time frame for each countermeasure
Effort level of countermeasure
Criteria?
WA or fix?
Use DAR process
Define approver
list of countermeasures
chosen countermeasures
root cause
Perform countermeasure as described in ticket
Search issue in <redmine> or <knowledge-based tool>
Found
Verify countermeasure is working and issue is solved
Not working
A
Working
Register issue to <redmine> or <knowledge-based tool>
Investigate issue
Determine root cause of issue
Categorize and Prioritize Issue
Determine possible countermeasures to address the issue
Select best countermeasure
Apply countermeasure
Verify if countermeasure solves the issue
OK
NG
Documentation (Update <redmine>)
Not found
transfer prioritization to above process.
need to create process
define the action item
guideline:
1. do not use company name
2. can use company email (clarify)

## Notes
How to gather know-how:
Installation Issues:
--------------------
0. Search issue in <redmine> or <knowledge-based tool>
>> How to search?? what keyword or category?
if issue is found in <redmine> or <knowledge-based tool>:
- perform countermeasure as indicated
- confirm if countermeasure is working and issue is solved
- if countermeasure is working, end of process
- else, proceed to next step
else, proceed to next step
1. Register issue to <redmine> or <knowledge-based tool>
- Issue Summary
- Issue Detail
- Software version
- etc.. (needed info is to be defined)
2. Determine root cause of issue:
A. Config
- check if all previous steps was followed accordingly
B. Network setup
C. Server setup
- Is the HW and SW resource indicated in Installation Manual followed? (use of VMs instead of PMs)
- Was the setup of HW and SW resources correct? (memory, # of cpus)
-
3. Categorize issue
- Severity
> Critical
> High
> Medium
> Low
- Field of concern
> Finance
> Regulatory
> Legal
3. Determine possible countermeasures to address the issue
- How to determine?
> Search the internet
> Ask persons with experience to the OSS
> Ask in community
> Source code trace
>
- assess each countermeasures, its pros and cons
- what are the risks associated to each countermeasure
- time frame for each countermeasure
- effort level of countermeasure
4. Select best countermeasure.
- Categorize countermeasure,
a. WA or fix
- Criteria
-
5. Apply countermeasure and verify if countermeasure solves the issue
6. Documentation (Update <redmine>)
- list of countermeasures
- chosen countermeasures
- root cause
- categorize
-
===============================================================
- categorize issue, maybe this is applicable to others
> Critical
> High
> Medium
> Low
- prioritization
> Finance
> Regulatory
> Legal
- escalation
- decide whether the countermeasure to the issue should be added in Wiki
to strengthen Wiki output
- known issues - how to handle??

## Knowledge Mgt Software List
Knowledge Management Systems
No. | Name | Company | Open-source | Features
1 | Confluence | Atlassian | No
2 | OpenKM
3 | KnowMax
4 | SpiceWorks |  | Yes | N/A. This is for IT (HW) issue management.
5 | phpMyFAQ
6 | PHPKB
7 | Raneto
8
9