## OSS Investigation Process_backu (hidden)
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Input | Ouput | Remarks
1 | Ticket Handling Process |  | Client | New | 1) Target OSS 2) OSS requirement 3) Duration or deadline | New Ticket | Tracker: Consultancy
PM/PL
|  |  | PM/PL | Assigned | New Ticket | Assgined ticket | If task involves multiple OSS investigation, PM/PL should create subtasks such that there is 1 subticket for 1 OSS.
2 | Estimation Process Review Process |  | Engineer | InProgress | Requirements described in ticket or uploaded requirements document | Requirements list | Engineer collects the OSS requirements based on the ticket
|  |  | Engineer | Feedback | Q&A List | Email for clarification Updated redmine ticket | Member will solicit additional requirements from the client
|  |  | Client | Feedback | Email for clarification Updated redmine ticket | Q&A Response
|  |  | Engineer | Feedback | Q&A Response | Follow up Q&A / Confirmed Q&A | Review the answers/comments to Q&A Make a follow-up question if there are still unclear parts or proceed to Estimation if there Q&A is already OK
|  |  | Engineer | InProgress | Requirements list | Initial Research Notes | Perform an initial research based on requirement to use as basis for estimation Check if there is an existing infromation in OSS wiki.
|  |  | Engineer | InProgress | Requirements list Initial Research Notes | Activity List and Schedule | Create an investigation plan and its schedule
|  |  | PM/PL | InProgress | Requirements List Activity List and Schedule Initial Assessment | Review Comments | Review the plan and schedule in reference to requirements list
|  |  | Engineer | Feedback | Requirements List Activity List and Schedule Initial Assessment | Updated ticket | Update the ticket with the initial investigation and schedule
|  |  | Client | Feedback | Updated ticket (Proposal) | Updated ticket (comments/approval) | Client reviews the initial assessment, schedule and requirements list Client should give comments if there are unclear/incorrect items or give approval if its client agrees with the proposal
|  |  | Engineer | InProgress | Requirements List Activity List and Schedule Initial Assessment | Investigation Report Research Documentation | Refer to Investigation Process for the details
3 | Investigation Process Review Process
|  |  | Client | Feedback | Investigation Report Research Documentation | Client Confirmation or Client Comments | Client reviews the investigation report and research documentation If client has comments or additional requests, the ticket will be updated with the additional comments/requirements. And the process will go back to investigation. If all are OK wiki will be updated and the ticket will be closed.
4 | Wiki Update Process |  | Engineer | Resolved | Research Documentation | New Wiki Site or Updated Wiki Site | Refer to Knowledge Management Process on how to create/update wiki page
5 | Ticket Handling Process |  | PM/PL | Closed | Client Confirmation/Decision | Closed Ticket
|  |  | OSS evaluation/Investigation |  | Problem
|  | Planning and Estimation | Gathering initial details |  | Replication
Duplicate Issue
Estimate
Overall Task Flow
| Processes Involved | Flow | Action | Status
| Ticket Handling Process |  | Create Ticket | New
0%
|  |  | Assign Ticket | Assigned
0%
| Estimation Process |  | Update Ticket | InProgress
|  |  | 1-99% | Feedback
Done?
|  | 20% |  | Resolved?
Cancelled?
Rejected?
Investigation process
90%
Wiki Process
95%
|  |  | Close Ticket | Closed
| Ticket Handling Process |  | 100%
Ticket Registration
Ticket Assignment
Perform Estimation
no modifications needed
some modifications needed
re-investigate
Gather Requirements
cancel request
Perform Initial Research
Perform Detailed Investigation
Update Ticket
Review Req List and Schedule
Client Confirmation
estimate is not OK
Client Assessment
Wiki Update
Close Ticket
cancel request
Request additional info from client
Client provides response to clarification
Verifies answers to Q&A
Info sufficient
Need additional details
Need additional details
Info sufficient
Ticket Registration
Ticket Assignment
Initial Assessmenet and Estimation
Perform Detailed Investigation
Wiki Update
Close Ticket

## Title Page
NEC Telecom Software Philippines, Inc. |  | OSS Q&A Support Process | Registration No.
|  |  | Version No. | 00.01.00
|  |  | Date | 2017-05-17
|  |  | No. of Sheets | 4
|  |  | Approved | Reviewed | Prepared
|  |  |  | NSP-Matsumoto NSP-Jay NSP-May NSP-Verg | NSP-Mari
Table of Contents
Sheet No. | Sheet Title
1 | Title Page
2 | Revision History
3 | Introduction
4 | OSS Q&A Support Process

## Revision History
Revision History
Version No. | Date | Author | Reviewer | Revision Summary
00.00.01 | 2017-05-12 | NSP-Mari |  | · Draft
00.00.02 | 2017-05-16 | NSP-Mari | NSP-Matsumoto NSP-Jay NSP-May NSP-Verg | · Based on NSP Review Comment
00.00.03 | 2017-05-17 | NSP-Mari | NSP-Matsumoto NSP-Jay NSP-May NSP-Verg | · Based on NSP Confirmation

## Introduction
OSS Q&A Support Process
1. Overview
As OSS seeks to support and accommodate a variety of clientele, the inquiries and support needs from these Clients also increase.
Through Q&A, we aim to answer and accommodate all customer-related concerns and inquiries and to make these information available to those who can use it.
2. Purpose
To provide a process and/or guidelines on how to perform OSS Q&A Support.
3. Scope
This process is applicable to OSS Q&A Support activities of the OSS Team.
4. Definition and Acronyms
| Term | Definition
| OSS | Open-Source Software - is a software with source code that anyone can inspect, modify, and enhance.
| Q&A | Question and Answer - Questions from the Clients to be answered by OSS Team.
5. Roles and Responsibilities
| Role | Responsibility
| Project Manager | • The project manager assigned to handle the project
• Reviews the estimates and project plan
• Negotiates with the client
| Project Leader | • Creates the estimates and the project plan
| Project Member | • Responsible for providing inputs necessary for project planning (e.g. provide estimates) and commits to the plan
5. References
None.

## OSS Q&A Support Process
| Entry Criteria | 1. Client created a redmine ticket for a question about a specific OSS 2. Client asked a question about a specific OSS through email 3. PM/PL created a ticket for a question about a specific OSS Please see Q&A Format sheet for the request format.
| Exit Criteria | 1. The ticket is closed because the question is answered and the client verified that there are no more followup questions 2. The question is cancelled by client/PM/PL
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Input | Ouput | Remarks
1 | Ticket Handling Process |  | Client | New | Relevant information as specified in the Q&A Format. (Refer to Q&A Format sheet) | New Ticket | Tracker: Q&A
PM/PL
|  |  | PM/PL | Assigned | New Ticket | Assigned ticket | Ticket is assigned to OSS Engineer
2 | Requirements Development |  | OSS Engineer | InProgress | Assigned Ticket | Assigned Ticket | Engineer checks if mandatory information is contained in the ticket If information is sufficient, proceed to Planning and Estimation
|  |  | OSS Engineer | Feedback | Assigned Ticket | Clarification addressed to the Contact Person | Engineer will solicit mandatory information from the client. Clarification will be done depending on the "[Preferred Communication Medium]" specified by the Client (whether it's through Redmine or e-mail). Engineer should input the clarifications in the Redmine ticket. If Client prefers Redmine, Engineer assigns the ticket to the Client's Contact Person. If Client prefers e-mail, Engineer sends an email, containing the clarifications, to the Client's Contact Person.
|  |  | Client | Feedback | Clarification details (through email or Redmine) | Answers to the clarifications (through email or Redmine) | If through Redmine, Client answers the clarifications by adding a note in the ticket and assigns the ticket to NSP OSS Engineer. If through e-mail, Client replies in the clarification email.
|  |  | OSS Engineer | Feedback | Answers to the clarifications (through email or Redmine) | Completely Filled-up Ticket | Review the Client's answers. If there are unclear parts, make a follow-up question. If answer is enough, Proceed to Planning and Estimation. If answer was sent through email, OSS Engineer updates the Redmine ticket.
3 | Planning and Estimation Process |  | OSS Engineer | InProgress | Completely Filled-up Ticket | Research Notes | Check if there is an existing information in OSS wiki. If there is, proceed to Step 5 Report Creation Process If none, perform an initial research, based on the information in the ticket, to use as basis for estimation.
|  |  | OSS Engineer | InProgress | Research Notes | Initial Assessment Estimation Document (Schedule) | Create an investigation plan and its schedule (Refer to Estimation Process for details on how to create the Estimation Document) *This may be optional if the question can be answered right away (within 1～2 days).
|  |  | PM/PL | InProgress | Estimation Document Initial Assessment | RRC (Review Comments) | Review the schedule and initial assessment whether these are according to Client's request *This may be optional if the question can be answered right away (within 1～2 days).
|  |  | OSS Engineer | Feedback | Estimation Document Initial Assessment | Updated ticket (with Schedule) | Update the ticket with the initial investigation and schedule *This may be optional if the question can be answered right away (within 1～2 days).
|  |  | Client | Feedback | Initial Assessment & Schedule (through email or Redmine) | Approval (through email or Redmine) | OSS Engineer informs the Client about the initial assessment and schedule through Redmine or email, depending on Client preference. Client reviews the initial assessment and schedule Client should give comments if there are unclear/incorrect items or give approval if its client agrees with the schedule *This may be optional if the question can be answered right away (within 1～2 days).
4 | Investigation Process |  | OSS Engineer | InProgress | Estimation Document Initial Assessment | Process Classification | OSS Engineer determines whether this request is one of the following processes. - Investigation Process - Problem Investigation Process - Evaluation Process - Consulting Support Process If yes, OSS Engineer creates a new corresponding ticket and relates it to this Q&A ticket. (Refer to the following for the processes: OSS Investigation Process.xlsx OSS Problem Investigation Process.xlsx OSS Evaluation Process.xlsx OSS Consulting Support Process.xlsx) If no, proceed to "Search for additional information"
|  |  | OSS Engineer | InProgress | Research Notes Process Classification | Verified Answer | Performs the corresponding OSS Process. *This may be optional if there is no new corresponding task created. That is, if the process is still Q&A Process.
|  |  | OSS Engineer | InProgress | Research Notes | List of References Reference Documents | *This may be optional if Q&A has related OSS Process.
|  |  | OSS Engineer | InProgress | List of References | Research Notes, Knowledge | Read and study the question/s carefully. Read and study the collected references and look for answers to the question/s. Check if answer/s is/are enough. If not, search for additional material and look for answers. Record all issues/problems known during study/research
5 | Report Creation Process |  | OSS Engineer | InProgress | Research Documentation Investigation Report (from the Investigation Task) | Answer to the question | Create answers to questions Organize notes to cater to wiki sections/contents or customer specified output
|  |  | PM/PL | InProgress | Research Documentation Investigation Report | RRC (Review Comments/Confirmation) | Check if investigation report answers the client's question Check if documentation is enough (Refer to Review Process for the details of review procedure/guidelines)
|  |  | OSS Engineer | Feedback | Research Documentation Investigation Report | Updated Ticket (with Investigation Result/Answer) | OSS Engineer updates ticket with investigation report/answer If Client prefers Redmine, Engineer assigns the ticket to the Client's Contact Person. If Client prefers e-mail, Engineer sends an email, containing the investigation report/answer, to the Client's Contact Person.
|  |  | Client | Feedback | Investigation Result/Answer (through Redmine or e-mail) | RRC (Review Comments/Confirmation) | Client will assess if answer is enough. Ticket will be updated or an email will be sent whether client is satisfied with the answer or has follow-up questions. It is possible that re-investigation is needed based on client's followup questions or it is possible that the question will be cancelled or the ticket will be closed because the answer already satisfies the client.
6 | Wiki Update Process |  | OSS Engineer | Resolved | Investigation Report | Wiki Site (with new OSS or OSS update) | If information is already contained in Wiki, skip this step. (Refer to Knowledge Management Process on how to create/update wiki page)
7 | Ticket Handling Process |  | PM/PL | Closed | Client Confirmation/Decision | Closed Ticket
Ticket Registration
Ticket Assignment
Perform Estimation
no modifications needed
some modifications needed
Initial Data Gathering
cancel question
Perform Initial Research
Update Ticket
Review Initial Assessment and Schedule
Client Confirmation
estimate is not OK
Reflect investigation result to Wiki
Close Ticket
Request additional info from client
Client provides response to clarification
Verifies additional info
Info sufficient
Need additional details
Need additional details
Info sufficient
Create Corresponding Task
Create Answer
Review/Confirmation
Update Ticket
Client Confirmation
re-investigate
cancel request
some modifications needed
no modifications needed
result is OK
Determine correct OSS Process
Search for additional information
Search for answers

## Investigation Process (hidden)
Input | Schedule
Requirements List
Output | Investigation Report
Research Documentation
1 |  | Collect information/references from
1) OSS Wiki Site (if available)
2) Reference documents from other NSP project groups
3) Official OSS website
4) Internet (other references)
2 |  | Read and study the collected references (create notes)
Check the strong and weak points of the OSS
Perform analysis if OSS is suitable to use or if there are better OSS
Check if references gathered has enough information for the OSS requirements
If not, search for additional material and study them
Record all issues/problems known during study/research
3 |  | Check harware requirements if it is available in OSS Tech Center
Check software requirements if it can be acquired from internet(free) or from client(with license)
If hardware/software requirements is not available, arranged use of client environment
Get commitment on date and time of environment use by OSS Tech Center
If hardware/software requirements is available, download the OSS and other softwares
Install OSS either from source or repository
Install the OSS using the mandated method of the client (yaml, rpm, ,etc)
Record all issues/problems known during study/research
4 |  | Configure the OSS based on the indicated setup in requirements list
If there are no indicated setup in the requirements list, decide the best setup based on the requirements
Record all issues/problems known during study/research
5 |  | Create test specification
|  | Execute test items |  |  | Are we going to use tool?
|  | Collect evidence during testing (screenshot, logs, packet capture) |  |  | What tool to use?
Record all issues/problems known during study/research
6 |  | Create investigation report
Organize notes to cater to wiki sections/contents or customer specified output
7 |  | Check if investigation report is complete based on requirements
Check if documentation is enough
Refer to review process sheet for the details of review procedure/guidelines
8 |  | Update ticket with investigation report and research documentation
9 |  | Client will assess if investigation report is correct and complete
Ticket will be updated whether client agrees to the investigation report or updated based on client comments
It is possible that re-investigation is needed based on client comments or
it is possible that the request will be cancelled or
the ticket will be closed because investigation report already satisfies the client.
10 |  | Wiki site will be created/updated based on the investigation performed by the engineer.
11 |  | The request is cancelled as decided by client
OSS Default Contents for OSS Investigation
M/O | Description | Remarks
M | OSS Overview | This is a mandatory section. Discusses the short description about the OSS.
M | Architecture | This is a mandatory section. A diagram on showing its modules and its relationships.
M | Features and Functionalities | This is a mandatory section. Enumerates and discusses the OSS functionalities and features.
M | System Requirements | This is a mandatory section. List the hardware and software requirements of the OSS. Also list down the software dependencies.
M | Version Information | This is a mandatory section. List down the OSS versions and its supported features(or limitations).
M | Installation Procedure/Guide | This is a mandatory section. An installation guide for its supported setup.
M | System Configurations | This is a mandatory section. List/Diagrams of the different configurations supported by the OSS.
M | Use case | This is a mandatory section. Use cases supported by the OSS.
M | Limitations/Known issues | This is a mandatory section. Known bugs/limitations of the OSS.
M | License | This is a mandatory section. License information of the OSS. OSS can have a separate site for different types of License. And the Licence type can just be mentioned in the OSS overview.
O | Performance | This is an optional section but will become mandatory if indicated by client. Performance data can collected from official OOS website or benchmarking website or from actual testing.
O | Reliability | This is an optional section but will become mandatory if indicated by client. Realiability data can collected from officail OSS website or by research to other references.
O | Availability | This is an optional section but will become mandatory if indicated by client. Availability data can collected from officail OSS website or by research to other references.
O | Security | This is an optional section but will become mandatory if indicated by client. Security data can collected from officail OSS website or by research to other references.
O | Modifiability | This is an optional section but will become mandatory if indicated by client. Modifiability data can collected from officail OSS website or by research to other references.
O | Portability | This is an optional section but will become mandatory if indicated by client. Portability data can collected from officail OSS website or by research to other references.
O | Scalability | This is an optional section but will become mandatory if indicated by client. Scalability data can collected from officail OSS website or by research to other references.
O | System Components | This is an optional section but will become mandatory if indicated by client. System Components can collected from officail OSS website or by research to other references.
O | Technologies used | This is an optional section but will become mandatory if indicated by client. Technology used can collected from officail OSS website or by research to other references.
Overall Task Flow
| Processes Involved | Flow | Action | Status
| Ticket Handling Process |  | Create Ticket | New
0%
|  |  | Assign Ticket | Assigned
0%
| Estimation Process |  | Update Ticket | InProgress
|  |  | 1-99% | Feedback
Done?
|  | 20% |  | Resolved?
Cancelled?
Rejected?
Investigation process
90%
Wiki Process
95%
|  |  | Close Ticket | Closed
| Ticket Handling Process |  | 100%
How to Perform Review
PM/PL
Group
Peer
Client
Walkthrough
Desk Review
Self Check
POV
Spelling&Grammar
Content Relevance Review
Completeness (template as basis?)
Collect Information or References
Study and Record Notes
Install OSS
Configure OSS
Installation Verification
Create Investigation Ouput
Review/Confirmation
Update Ticket
some modifications needed
no modifications needed
Client Confirmation
some modifications needed
Reflect investigation result to Wiki
Cancel Request
Ticket Registration
Ticket Assignment
Initial Assessmenet and Estimation
Perform Detailed Investigation
Wiki Update
Close Ticket

## Estimation Process (hidden)
Pls. use NSP08-00000-TMP006_Project Estimation Template.xls and NSP08-00000-GDL003_Project Estimation Guideline.doc

## Investigation Process_old (hidden)
How to perform investigation/research
Phases | Description
Req Development | Determine the scope of the research based on information in the ticket
If the information in the ticket is not enough, inquire to the client
| Create a requirement list and get client confirmation [email, ticket update, face-to-face review] |  |  |  | Steps
| Perform initial research for estimation and feasibility check of client requirement and specified OSS |  |  |  | Determine the research scope
Research | Collect information regarding the target OSS from existing documents |  |  |  | Determine mandatory and optional requirements
| Collect information from other project groups |  |  |  | Determine the timeline
| Collect information from internet (visit official website of OSS, visit other sites for reference, check reviews/comparisons) |  |  |  | Write a research questions
| Check completeness of acquired information using OSS investigtion template [refer to Appendix A. OSS Investigation Template] |  |  |  | Collect possible sources
| Check completeness of information based on client mandated output (if available) |  |  |  | Begin reading in detail
| Commit notes, output document daily (for PM/PL desk review) |  |  |  | Take notes on what you read
| Perform installation/configuration of OSS based on customer environment (if there is time and environment is available) |  |  |  | Evaluate your information (installation/configuration/testing)
Record all the sites used as reference
Concentrate information collection based on the requirements list
Record known issues encountered for documentation
Analysis | Perform feasibility analysis of requirements based on acquired OSS information
Create an output document based on customer requirements or customer requested output
How to check successful installation
How to check successful configuration
| Operation Management | Market Research | Description | Method
ViewPoints/Document Contents | Mandatory | Mandatory | OSS Overview
| Mandatory | Mandatory | Architecture
| Mandatory | Mandatory | Features and Functionalities
| Mandatory | Mandatory | System Requirements
| Mandatory | Mandatory | Version Information
| Mandatory | Mandatory | Installation Procedure/Guide
| Mandatory | Mandatory | System Configurations
| Mandatory | Mandatory | Use case
| Mandatory | Mandatory | Limitations/Known issues
| Mandatory | Mandatory | License
| Optional | Mandatory | Performance | Collect performance information through website research For advance performance data collection refer to <document name here>
| Optional | Mandatory | Reliability
| Optional | Mandatory | Availability
| Optional | Mandatory | Security
| Optional | Mandatory | Modifiability
| Optional | Mandatory | Portability
| Optional | Mandatory | Scalability
| Optional | Mandatory | System Components
| Optional | Mandatory | Technologies used
Research | Notes
References (books, url)
Testing | Screenshot
Logs
| Packet Capture |  |  |  |  | Check the wiki | Collect Basic Information
Collect Advance Information (if available)
Check the ticket for the requirements stated by the client
Create a requirements list
Solicit from client if there are other needed information mentioned (ticket, email, lync)
There should be evidence for the solicited requirements, either email or recorded conversation
Perform a short research about the feasibility of the request
Create an estimate to check if the requested end date can be met
Update the ticket with initial investigation result and estimate
If the end scope is too big to finish on the required date
Suggest a new schedule so on when it can be finished
Or list down requirements that can be excluded so that the activity can fit on the given schedule
When the schedule and scope are agreed with the client
Perform detailed investigation based on the requirements list
Refer to Knowledge Management Process on how to perform detailed investigation
how to determine if the information is not enough
how to collect data?
write in redmine (not adivisable for research activities)
write to a new document, store in repo and note the location in redmine ticket
write to a new document and attach to redmine ticket
Requirements
Gathering
Perform Initial Investitgation
Create an Estimate
Feedback to client
Perform Detailed Investigation
Investigation
Process
Check the OSS Wiki Site
Check the official OSS Site
Check reference documents from other NSP groups
Check other Internet sites for reference
Check sites for OSS reviews or comparison
Perform Installation and configuration

## OSS Investigation Process_old (hidden)
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Input | Ouput | Remarks
1 | Ticket Handling Process |  | Client | New | Target OSS | New Ticket | New OSS investigation request Ticket can be of the following type: Consultancy
Duration/Delivery Date
Intended Usage, Required Output
|  |  | PM/PL | New |  |  | New OSS for knowledge building is identified Ticket can be of the following type: Consultancy
|  |  | PM/PL | Assigned |  |  | Assigns developer to investigate the ticket
2 | Estimation Process Review Process |  | Developer |  | Client Requirements | Initial Investigation Result | Perform initial investigation and create estimate/schedule for the new OSS | What will be the status when developer starts initial investigation
Estimate
|  |  | PM/PL |  | Initial Investigation Result | Review Comments | Review estimate and schedule
Estimate
|  |  | Developer | Feedback |  | Updated Investigation/ | Update ticket with schedule/estimate and initial information
Updated Estimate
|  |  | Client | Feedback |  |  | Check if estimate is OK, decide to continue or not based on initial information
Ticket is updated with
client feedback
3 | Investigation Process Review Process |  | Developer | InProgress | Client Requirements | Research Report ( Customer | Perform research/investigation
or OSS default format)
|  |  | PM/PL | InProgress |  |  | Perform review based on investigation result
[5 empty] | Research Report | Review Comments
|  |  | Developer | InProgress |  | Updated Research Report | Perform rework based on review comments
|  |  | PM/PL | Done |  |  | Perform confirmation of review comments
|  |  | Client | Resolved |  |  | Client agrees with the investigation result and there are no futher requests/comments
4 | Wiki Process |  | Developer | Resolved |  | New Wiki Site | Create/Update Wiki based on the approved contents of investigation
or updated wiki site
5 | Ticket Handling Process |  | PM/PL | Closed |  |  | Close Ticket
Ticket Registration
Ticket Assignment
Research/Investigation
Review
Rework
Confirmation
Create/Update Wiki
Close Ticket
Perform Estimation
Update Ticket
Review Estimate
Confirm Estimate
estimate is not OK
estimate is OK
cancel request
proceed with investigation
for re-estimation
no modifications needed
some modifications needed
some modifications needed
no modifications needed
Close Ticket
Client confirmation

## Q&A Format
Q&A Format
Question Part: (to be filled-up by Client)
[Project Name] :
[Target OSS] :
[Contact Person] :
[Issued Date] :
[Expected Answer Date] :
[Preferred Communication Medium] : <Redmine/Email>
[CP Available?] : <Yes/No>
[Can NSP access Client Env't?] : <Yes/No>
[Question] :
Answer Part: (to be filled-up by NSP)
[Answered By] :
[Answered Date] :
[Answer] :