## Problem Investigation Activity1 (hidden)
| Entry Criteria: | An issue was encountered during installation/configuration of OSS
| Exit Criteria: | Issue was resolved and know-how was documented.
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Inputs | Outputs | Remarks | Documents
1 | Ticket Handling Process |  | Client | New |  |  | Register issue in redmine
1 |  |  | PM/PL | Acknowledged |  |  | Check if details needed are filled-up properly.
1 |  |  | PM/PL | Acknowledged |  |  | Check if OSS Technical Center has knowledge to the OSS related to the registered issue
1 |  |  | PM/PL | Acknowledged
1 |  |  | PM/PL | Assigned |  |  | Assign ticket to developer/in-charge
1 |  |  | PM/PL | Assigned
1 |  |  | PM/PL | Assigned
2 | Initial Investigation Process |  | Developer | Assigned |  |  | Perform initial investigation
2 | Duplicate Entry Checking Process | [5 empty] | - prepare environment (replicate client's environment) and other known necessary resources needed for investigation
2 | Verification Process | [5 empty] | Problem classification
2
2
2 | [6 empty] | Check issue if it has duplicate or information is already in Wiki
2
2
2
2 | [6 empty] | Check status of duplicate issue if resolved or not
2
2
2
2
2
2 | [6 empty] | Verify duplicate issue's solution on the current issue reported
2
2
2
2
3 | Estimation Process | [5 empty] | Create estimate/schedule for the problem investigation and solution
3
3
3
3
3
3
3
3
3
3
3
4 | Investigation Process
4 | Review Process
4 | Protoyping Process
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
5
5
5
5
5
Ticket Registration
Ticket Assignment
OSS already investigated
OSS not yet investigated
Perform OSS investigation activity
Duplicate issue checking
Initial Investigation
Environment and issue can be replicated
Environment and issue can not be replicated
Send feedback to client
issue has duplicate
issue is new
Verify solution
issue is not solved
issue is solved
Perform Estimation
Duplicate issue status checking
issue is not yet solved
issue is already solved
Update Ticket
Review Estimate
Confirm Estimate
estimate is not OK
estimate is OK
cancel request
for re-estimation
Research/Investigation
Review
Rework
proceed with investigation
no modifications needed
some modifications needed
some modifications needed
no modifications needed
Client confirmation
Problem Solution
Confirmation
client does not agrees to proposal
Close Ticket
client agrees to proposal
Create/Update Wiki

## Title Page
NEC Telecom Software Philippines, Inc. |  | Problem Investigation Process | Registration No.
|  |  | Version No. | 00.00.02
|  |  | Date | 2017-06-01
|  |  | No. of Sheets | 4
|  |  | Approved | Reviewed | Prepared
NSP-Rap NSP-Steve NSP-May
Table of Contents
Sheet No. | Sheet Title
1 | Title Page
2 | Revision History
3 | Introduction
4 | Problem Investigation Process

## Revision History
Revision History
Version No. | Date | Author | Reviewer | Revision Summary
00.00.01 | 2017-04-18 | NSP-Rap |  | · Draft
00.00.02 | 2017-06-01 | NSP-May |  | · Updated the following sheets: a. Introduction - to update the Definition and Acronyms section. b. Problem Investigation Process - to update the subprocesses: Ticket Handling, Requirements Development, Planning and Estimation, and Report Creation.

## Introduction
Problem Investigation Process
1. Overview
The OSS Problem Investigation Process serves as a guide in performing the client request for OSS Problem Investigation.
2. Purpose
To provide a process and/or guidelines on how to perform Problem investigation.
3. Scope
This process is applicable to Problem Investigation activities of the OSS Team
4. Definition and Acronyms
| Term | Definition
| OSS | Open-Source Software - is a software with source code that anyone can inspect, modify, and enhance.
This symbol depicts another Process or Subprocess within this document or in another document. This symbol is also used as another Task or Activity within this document or in another document.
This symbol is the tasks within this Process or Subprocess.
5. Roles and Responsibilities
| Role | Responsibility
| Project Manager | • Responsible for performing the tasks assigned to Incharge PM
| Project Leader | • Responsible for performing the tasks assigned to Incharge PL
| Project Member | • Responsible for performing the tasks assigned to Incharge OSS Engineer
| Client | • Responsible for performing the tasks assigned to Incharge Client
5. References
None.
Task
Process or Subprocess
Task or Activity

## Problem Investigation Process
| Entry Criteria: | An issue/problem was encountered by the client during installation/configuration of OSS
| Exit Criteria: | The issue/problem was resolved and know-how was documented.
Task # | SubProcess | Process Flow | Incharge | Ticket Status | Inputs | Outputs | Details
1 | Ticket Handling |  | PM/PL | InProgress | OSS Support Client request | Updated Redmine ticket | Refer to the "OSS Common Process - Ticket Handling Subprocess" for details on performing the Ticket Handling tasks.
2 | Requirements Development |  | OSS Engineer | InProgress | Updated Redmine Ticket | Requirements List reviewed and approved | Refer to the "OSS Common Process - Requirements Development Subprocess" for details on performing the Requirements Development tasks. Prior to performing the task "Planning and Estimation Subprocess" perform first the other Requirements Development tasks below.
|  |  | OSS Engineer | InProgress | Problem details/notes with additional/updated details based on Q&A; Wiki, etc. | Information if duplicate or not | Check if reported problem has a duplicate or existing issue reported
|  |  | OSS Engineer | InProgress | Information if duplicate or not |  | Proceed to performing initial investigation if issue is new. Otherwise, proceed to next step
|  |  | OSS Engineer | InProgress | Duplicate issue ticket | Information if duplicate issue is resolved or not | Check status of the duplicate issue if it is already resolved or not
|  |  | OSS Engineer | InProgress | Information if duplicate issue is resolved or not |  | Proceed to performing initial investigation if duplicate issue is resolved. Otherwise, proceed to next step
|  |  | OSS Engineer | InProgress | Duplicate issue solution | Information if duplicate issue solution is applicable to newly reported issue | Verify duplicate or existing issue solution if it solves the newly reported issue
|  |  | OSS Engineer | InProgress | Information if duplicate issue solution is applicable to newly reported issue | OSS Report | Proceed to creating solution report if duplicate issue solution is applicable. Otherwise, proceed to next step
3 | Planning and Estimation |  | OSS Engineer | InProgress | Requirements List reviewed and approved | Client approved Estimates and Plans | Refer to the "OSS Common Process - Planning and Estimation Subprocess" for details on performing the Planning and Estimation tasks.
4 | Problem Investigation |  | OSS Engineer | InProgress | SW/HW resource request list | SW/HW resources | Perpare test environment for replication Acquire SW/HW required for test environment
|  |  | OSS Engineer | InProgress | SW/HW resources | SW/HW resources with installed OS, MW, etc | Setup HW and install required OS, MW
|  |  | OSS Engineer | InProgress | SW/HW resources with installed OS, MW, etc | SW/HW resources with installed OS, MW, etc with installed OSS and its depencies, snapshot of VM | Install OSS, dependencies, create snapshot of VM
|  |  | OSS Engineer | InProgress | SW/HW resources with installed OS, MW, etc with installed OSS and its depencies, snapshot of VM | Configured environment bsed on client's environment or as expected | Configure according to client's current environment/ expected environment
|  |  | OSS Engineer | InProgress | Configured environment bsed on client's environment or as expected | Correct test bed for problem replication | Verify test bed correctness using simple test scenarios
|  |  | OSS Engineer | InProgress | Problem replication procedure | Replicated problem | Replicate problem reported using replication procedure provided by client
|  |  | OSS Engineer | InProgress | Problem details/notes/Q&A info/ Initial Problem Investigation notes | Root cause | Determine the root cause of the issue and record it in redmine
|  |  | OSS Engineer | InProgress | Problem details/notes/Q&A info/ Initial Problem Investigation notes | Category and priority details | Determine the category and priority of the problem and record it in redmine Note: Categorization and prioritization criteria is still TBD.
|  |  | OSS Engineer | InProgress | Problem details/notes/Q&A info/ Initial Problem Investigation notes; plus additional information | List of possible solutions/ workarounds with comparison | List possible solutions and compare identified solutions using DAR
|  |  | OSS Engineer | InProgress | List of possible solutions/ workarounds with comparison | Selected solution | Based on DAR criteria, select the best solution to the problem Note: DAR criteria is still TBD.
|  |  | OSS Engineer | InProgress | Selected solution | Verified test bed | Verify the best solution selected by testing based on the replication procedure
5 | Report Creation |  | OSS Engineer | InProgress | Any of the following outputs after performing the OSS Task: - Research Documentation - Investigation Report - Evaluation Report | Update Wiki site | Refer to the "OSS Common Process - Report Creation Subprocess" for details on performing the Report Creation tasks.
6 | Ticket Handling Process |  | OSS Engineer | Done | Updated Wiki Site | Status update | After Wiki has been created/updated, change status of ticket to done
|  |  | PM/PL | Closed | Redmine Ticket status issued by client is done | Status update | If ticket is done, it triggers for PM/PL to update ticket status to closed
Duplicate issue checking
issue has duplicate
issue is new
Verify solution
not applicable
applicable
Duplicate issue status checking
issue is not yet solved
proceed with investigation
Verification NG
Close Ticket
Acquire SW/HW required
Install OSS
Setup HW , OS, SW, MW
Configure environment
Verify test bed
Execute problem replication procedure
Determine root cause
Categorize and Prioritize the problem
Determine possible solutions
Not replicated
Replicated
Select best solution from the list
Verify best solution
Verification OK
Ticket Status Update
issue is solved
Ticket Handling
Subprocess
Requirements Development
Subprocess
Planning and Estimation
Subprocess
Report Creation
Subprocess