## Ticket handling process
Ticket State Transition Diagram
Criteria for changing ticket states
Current State | New State | Criteria
New | Assigned | PM/PL assigned a developer to process the task
| Cancelled | Client/PM/PL cancelled the request
Assigned | Feedback | Initial investigation and estimation is finished
InProgress
| Cancelled | Client/PM/PL cancelled the request
Feedback | Assigned
| InProgress | Client approved the initial investigation result and estimate
Done
Resolved
| Cancelled | Client/PM/PL cancelled the request
| Rejected | Client rejected the initial investigation or estimate
InProgress | Done | Developer finished the investigation. Investigation result is review and confirmed.
Feedback
| Cancelled | Client/PM/PL cancelled the request
Rejected | Feedback | Re-investigation or re-estimation is finished
| Cancelled | Client/PM/PL cancelled the request
Done | Resolved | Client confirms investigation result and there are no further clarifications/questions/comments
Feedback
| Closed | No additional request or comments was received X days after the end of investigation
| Cancelled | Client/PM/PL cancelled the request
Resolved | Closed | No further requests/comments/clarifications received from client after X days
| Feedback | Additional request/comments/clarifications were received from client
| Cancelled | Client/PM/PL cancelled the request
Cancelled | Closed | Ticket was not re-opened X days after status was changed to cancelled
Feedback
Ticket Registration Procedure
1) Access the ticket management system via redmine (or similar tool)
http://www.ntsp.nec.co.jp/oss-tc/redmine/projects
2) Fill-up following fields
Fields | Description |  |  |  | Remarks
Target OSS | The target OSS for investigation |  |  |  | can be multiple OSS or 1 ticket 1 OSS? | M
Usage of OSS | The intended usage of OSS or its requirements |  |  |  | can be stated or can be attached document | M
Expected Output | Default(OSS team format), custom (client format) |  |  |  | if custom sample document should be attached | M
Delivery Date | The expected date of output delivery |  |  |  | end date or duration or start&end date | O
3) Create Ticket
4) Email will be notified to client via redmine when the ticket is created
5) Default assignment of task will be to PM/PL
6) Default status of task is New
Note:
*1 Ticket registration can be performed by Client, PM/PL
If request from client is informed through email, ticket registration will be performed by PM/PL
*2 The policy for client task request is 1 task 1 ticket
If ticket registration is performed by client and task specified is more than 1
Then PM/PL should create subtasks such that 1 task will have 1 ticket
*3 1 OSS will have 1 corresponding project
An OSS project could be linked to 1 or more client requests
This will be used for OSS internal processing only and cannot be seen by client
Ticket Assignment Procedure
1) Check if tracker assigned is correct
2) Check member availability
3) Determine ticket action (assign/reject/negotiate)
Refer to the table below for judging based on availability, duration and max req reached
Task Duration | Availability | Max Req Reached | Action | Remarks
< 1 day | O | O | Assign Member
| O | X | Assign Member
| X | O | Reject Request | No available manpower
| X | X | Negotiate | Inform about earliest manpower availability
> 1 day | O | O | Reject Request | No available manpower
| O | X | Assign Member
| X | O | Reject Request | No available manpower
| X | X | Negotiate | Inform about earliest manpower availability
Ticket Updating Procedure
1) Update is performed when at any ticket status except closed
2) Update can be performed for any of the following actions
A) Changing of ticket state
B) Changing the schedule
C) Adding notes
D) Adding a link
E) Adding issue
F) Updating progress
Progress Updating Rule
State | Progress | Remarks
New | 0%
Assigned | 0%
Feedback | - | will retain previous progress
InProgress | 1-89% | Creation Finished (1-60%) OSS Team Review Finished (65%) OSS Team Review Rework Finished (70%) OSS Team Confirmation Finished (75%) Client Review Finished (80%) Client Review Rework Finished (85%) Client Confirmation Finished (90%)
Done | 90%
Resolved | 95%
Rejected | 100% | Closed(Not resolved)
Cancelled | 100% | Closed(Not resolved)
Closed | 100% | Wiki update is already finished
Ticket Closing Procedure
1) Criteria for Closing task
State | Wiki | Additional Criteria
done | done | No request/comments/questions after XX days
resolved | done | N/A
cancelled | N/A | No request/comments/questions after XX days
New
Assigned
Closed
Cancelled
Done
InProgress
Feedback
Resolved
Rejected